## SIGNAL_backlog
corridor_id | asset_id | defect_type | severity_code | detected_date | due_date | estimated_block_hours | speed_restriction_kmph | requested_window_start | requested_window_end
COR-MAKM-KAVR | COR-MAKM-KAVR-signal | cable_fault | C | 2026-09-03 | 2026-10-07 | 4.22
COR-RYP-BZA | COR-RYP-BZA-signal | track_circuit_failure | C | 2026-09-10 | 2026-09-30 | 5.08
COR-SQF-HLX | COR-SQF-HLX-signal | track_circuit_failure | A | 2026-09-02 | 2026-09-07 | 2.92 | 20 | 2026-09-12 02:15 | 2026-09-12 05:10
COR-RAK-SPC | COR-RAK-SPC-signal | cable_fault | C | 2026-09-07 | 2026-09-29 | 2.29 |  | 2026-09-12 02:15 | 2026-09-12 04:32
COR-BZ-SFM | COR-BZ-SFM-signal | signal_relay_fault | B | 2026-09-02 | 2026-09-21 | 5.92
COR-MTO-RMW | COR-MTO-RMW-signal | signal_relay_fault | C | 2026-09-08 | 2026-10-23 | 5.88
COR-TPH-BKLE | COR-TPH-BKLE-signal | track_circuit_failure | A | 2026-09-02 | 2026-09-09 | 7.26 | 15 | 2026-09-12 01:30 | 2026-09-12 08:45
COR-BGN-KTP | COR-BGN-KTP-signal | cable_fault | B | 2026-09-06 | 2026-09-22 | 2.25
COR-MGS-VYN | COR-MGS-VYN-signal | cable_fault | A | 2026-09-02 | 2026-09-12 | 2.92 | 30
COR-VS-BRC | COR-VS-BRC-signal | track_circuit_failure | B | 2026-09-01 | 2026-09-13 | 2.02
COR-RJY-GVN | COR-RJY-GVN-signal | interlocking_fault | C | 2026-09-06 | 2026-09-29 | 6.3
COR-SNAP-RPMN | COR-SNAP-RPMN-signal | cable_fault | C | 2026-09-07 | 2026-09-29 | 6.27 |  | 2026-09-15 11:00 | 2026-09-15 17:16
COR-BRGW-DRGM | COR-BRGW-DRGM-signal | cable_fault | C | 2026-09-07 | 2026-10-22 | 3.96 |  | 2026-09-14 02:00 | 2026-09-14 05:57
COR-BNDM-ROU | COR-BNDM-ROU-signal | interlocking_fault | C | 2026-09-04 | 2026-10-05 | 3.13 |  | 2026-09-18 11:00 | 2026-09-18 14:07
COR-KNS-PHD | COR-KNS-PHD-signal | track_circuit_failure | B | 2026-09-02 | 2026-09-12 | 2.14
COR-PPE-MMB | COR-PPE-MMB-signal | signal_relay_fault | C | 2026-09-05 | 2026-10-02 | 2.78
COR-LTI-VJ | COR-LTI-VJ-signal | interlocking_fault | A | 2026-09-04 | 2026-09-09 | 5.73 | 30 | 2026-09-12 01:00 | 2026-09-12 06:43
COR-JYM-SZK | COR-JYM-SZK-signal | track_circuit_failure | A | 2026-09-06 | 2026-09-13 | 2.8 | 30
COR-KQN-ABI | COR-KQN-ABI-signal | interlocking_fault | B | 2026-09-02 | 2026-09-16 | 4.87
COR-AK-BSQ | COR-AK-BSQ-signal | track_circuit_failure | C | 2026-09-03 | 2026-10-03 | 3.34
COR-BANO-MCZ | COR-BANO-MCZ-signal | interlocking_fault | B | 2026-09-11 | 2026-09-28 | 3.79
COR-KAYR-LNT | COR-KAYR-LNT-signal | cable_fault | C | 2026-09-09 | 2026-10-14 | 7.07
COR-GNNA-BUP | COR-GNNA-BUP-signal | signal_relay_fault | B | 2026-09-11 | 2026-09-23 | 5.64 |  | 2026-09-13 01:30 | 2026-09-13 07:08
COR-KKHT-DBG | COR-KKHT-DBG-signal | interlocking_fault | C | 2026-09-10 | 2026-10-25 | 6.38
COR-NGL-THJ | COR-NGL-THJ-signal | interlocking_fault | B | 2026-09-08 | 2026-09-24 | 3.78 |  | 2026-09-19 23:15 | 2026-09-20 03:01
COR-ALP-PUC | COR-ALP-PUC-signal | signal_relay_fault | C | 2026-09-06 | 2026-10-06 | 4.19
COR-MTJL-GOPA | COR-MTJL-GOPA-signal | cable_fault | B | 2026-09-04 | 2026-09-17 | 6.75 |  | 2026-09-14 11:00 | 2026-09-14 17:45
COR-KYJ-MVLK | COR-KYJ-MVLK-signal | signal_relay_fault | C | 2026-09-05 | 2026-09-29 | 6.73 |  | 2026-09-14 22:15 | 2026-09-15 04:58
COR-GLE-BDCR | COR-GLE-BDCR-signal | track_circuit_failure | C | 2026-09-03 | 2026-10-01 | 7 |  | 2026-09-20 10:00 | 2026-09-20 17:00
COR-NRKP-TGB | COR-NRKP-TGB-signal | track_circuit_failure | B | 2026-09-05 | 2026-09-16 | 2.92
COR-AMPR-RMH | COR-AMPR-RMH-signal | signal_relay_fault | B | 2026-09-08 | 2026-09-28 | 4.75
COR-KEB-BLD | COR-KEB-BLD-signal | signal_relay_fault | C | 2026-09-08 | 2026-10-13 | 6.91 |  | 2026-09-15 14:30 | 2026-09-15 21:24
COR-JSME-KBQ | COR-JSME-KBQ-signal | track_circuit_failure | B | 2026-09-03 | 2026-09-18 | 2.04 |  | 2026-09-12 01:30 | 2026-09-12 03:32
COR-NDN-BEW | COR-NDN-BEW-signal | interlocking_fault | A | 2026-09-06 | 2026-09-12 | 7.13 | 20
COR-ALJN-MWUE | COR-ALJN-MWUE-signal | signal_relay_fault | C | 2026-09-02 | 2026-09-29 | 7.37
COR-DUM-RKR | COR-DUM-RKR-signal | interlocking_fault | A | 2026-09-07 | 2026-09-12 | 2.6 | 15 | 2026-09-12 23:15 | 2026-09-13 01:51
COR-BHLE-PJLE | COR-BHLE-PJLE-signal | interlocking_fault | C | 2026-09-11 | 2026-10-23 | 3.93
COR-BGP-AKN | COR-BGP-AKN-signal | track_circuit_failure | C | 2026-09-08 | 2026-10-09 | 5.54 |  | 2026-09-18 14:00 | 2026-09-18 19:32
COR-VJ-KVN | COR-VJ-KVN-signal | track_circuit_failure | A | 2026-09-10 | 2026-09-16 | 2.45 | 15 | 2026-09-12 01:00 | 2026-09-12 03:27
COR-PANP-S | COR-PANP-S-signal | track_circuit_failure | B | 2026-09-01 | 2026-09-14 | 3.88 |  | 2026-09-12 02:00 | 2026-09-12 05:52
COR-NZB-JKM | COR-NZB-JKM-signal | signal_relay_fault | C | 2026-09-01 | 2026-10-12 | 2.38
COR-RTGN-SAO | COR-RTGN-SAO-signal | track_circuit_failure | C | 2026-09-01 | 2026-10-02 | 6.2
COR-PRSR-SURP | COR-PRSR-SURP-signal | cable_fault | C | 2026-09-09 | 2026-09-29 | 4.63
COR-CTHR-KTHA | COR-CTHR-KTHA-signal | signal_relay_fault | A | 2026-09-07 | 2026-09-14 | 7.07 | 20
COR-CAM-PKA | COR-CAM-PKA-signal | cable_fault | B | 2026-09-01 | 2026-09-12 | 7.64
COR-NIM-BRMD | COR-NIM-BRMD-signal | cable_fault | A | 2026-09-01 | 2026-09-11 | 5.25 | 15
COR-BWX-BTI | COR-BWX-BTI-signal | track_circuit_failure | B | 2026-09-02 | 2026-09-19 | 4.14
COR-PLJ-LKD | COR-PLJ-LKD-signal | track_circuit_failure | B | 2026-09-08 | 2026-09-20 | 3.33
COR-GZM-MLDT | COR-GZM-MLDT-signal | cable_fault | B | 2026-09-07 | 2026-09-18 | 7.81 |  | 2026-09-12 14:30 | 2026-09-12 22:18
COR-CTHT-NWD | COR-CTHT-NWD-signal | cable_fault | C | 2026-09-11 | 2026-10-26 | 7.02
COR-LS-SUM | COR-LS-SUM-signal | signal_relay_fault | C | 2026-09-01 | 2026-09-26 | 3.75
COR-KKA-HWR | COR-KKA-HWR-signal | interlocking_fault | B | 2026-09-09 | 2026-09-26 | 7.52
COR-SHK-KSC | COR-SHK-KSC-signal | interlocking_fault | C | 2026-09-05 | 2026-10-14 | 6.35 |  | 2026-09-20 02:00 | 2026-09-20 08:21
COR-PGI-TA | COR-PGI-TA-signal | interlocking_fault | C | 2026-09-02 | 2026-10-06 | 7.76 |  | 2026-09-14 22:00 | 2026-09-15 05:45
COR-MER-SNKB | COR-MER-SNKB-signal | cable_fault | B | 2026-09-10 | 2026-09-27 | 7.97
COR-RDDE-HNN | COR-RDDE-HNN-signal | signal_relay_fault | B | 2026-09-09 | 2026-09-28 | 2.81
COR-KTPK-BKWA | COR-KTPK-BKWA-signal | signal_relay_fault | B | 2026-09-08 | 2026-09-28 | 4.16 |  | 2026-09-19 01:00 | 2026-09-19 05:09
COR-VN-KDY | COR-VN-KDY-signal | interlocking_fault | B | 2026-09-05 | 2026-09-20 | 3.63
COR-SCC-BVN | COR-SCC-BVN-signal | cable_fault | B | 2026-09-10 | 2026-09-20 | 2.9 |  | 2026-09-14 10:00 | 2026-09-14 12:54
COR-KORI-KUND | COR-KORI-KUND-signal | signal_relay_fault | B | 2026-09-05 | 2026-09-23 | 2.96 |  | 2026-09-20 11:15 | 2026-09-20 14:12
COR-KTKR-HER | COR-KTKR-HER-signal | interlocking_fault | B | 2026-09-08 | 2026-09-19 | 3.72
COR-SONW-WRS | COR-SONW-WRS-signal | cable_fault | A | 2026-09-01 | 2026-09-06 | 7.94 | 20 | 2026-09-12 11:30 | 2026-09-12 19:26
COR-TMPY-KAVR | COR-TMPY-KAVR-signal | cable_fault | C | 2026-09-01 | 2026-09-22 | 4.85
COR-MWY-DRR | COR-MWY-DRR-signal | interlocking_fault | C | 2026-09-10 | 2026-10-13 | 6.85 |  | 2026-09-20 22:00 | 2026-09-21 04:51
COR-KWB-BHV | COR-KWB-BHV-signal | signal_relay_fault | B | 2026-09-04 | 2026-09-19 | 6.31
COR-CLDR-SGDP | COR-CLDR-SGDP-signal | track_circuit_failure | C | 2026-09-11 | 2026-10-21 | 7.2
COR-KDPR-BAHN | COR-KDPR-BAHN-signal | signal_relay_fault | B | 2026-09-05 | 2026-09-18 | 6.85
COR-KSP-RBZ | COR-KSP-RBZ-signal | track_circuit_failure | C | 2026-09-02 | 2026-10-16 | 7.05
COR-JOP-ZBD | COR-JOP-ZBD-signal | interlocking_fault | A | 2026-09-05 | 2026-09-11 | 4.73 | 20
COR-PRDG-ACLE | COR-PRDG-ACLE-signal | signal_relay_fault | C | 2026-09-03 | 2026-09-23 | 4.73
COR-BUDI-SNAR | COR-BUDI-SNAR-signal | track_circuit_failure | B | 2026-09-08 | 2026-09-24 | 3.06
COR-DGB-KBM | COR-DGB-KBM-signal | track_circuit_failure | C | 2026-09-01 | 2026-10-04 | 2.04
COR-PLY-SRJN | COR-PLY-SRJN-signal | track_circuit_failure | B | 2026-09-06 | 2026-09-19 | 3.53
COR-ATM-DQG | COR-ATM-DQG-signal | track_circuit_failure | A | 2026-09-05 | 2026-09-12 | 2.78 | 30
COR-RJK-HZN | COR-RJK-HZN-signal | track_circuit_failure | B | 2026-09-01 | 2026-09-20 | 2.96 |  | 2026-09-18 00:00 | 2026-09-18 02:57
COR-GAW-KPE | COR-GAW-KPE-signal | signal_relay_fault | C | 2026-09-09 | 2026-09-30 | 4.26 |  | 2026-09-19 02:00 | 2026-09-19 06:15
COR-NXN-BANO | COR-NXN-BANO-signal | interlocking_fault | A | 2026-09-04 | 2026-09-13 | 7.8 | 20
COR-SRB-DRTP | COR-SRB-DRTP-signal | cable_fault | B | 2026-09-08 | 2026-09-22 | 5.09
COR-MTA-SGBJ | COR-MTA-SGBJ-signal | cable_fault | A | 2026-09-02 | 2026-09-07 | 6.2 | 20
COR-CKDL-HRNR | COR-CKDL-HRNR-signal | cable_fault | C | 2026-09-11 | 2026-10-09 | 6.43
COR-HNH-KAG | COR-HNH-KAG-signal | signal_relay_fault | A | 2026-09-04 | 2026-09-11 | 5.67 | 30
COR-GNS-VNK | COR-GNS-VNK-signal | cable_fault | A | 2026-09-02 | 2026-09-10 | 2.13 | 30
COR-RWJ-AMLI | COR-RWJ-AMLI-signal | cable_fault | B | 2026-09-07 | 2026-09-26 | 4.49
COR-KHRI-GMO | COR-KHRI-GMO-signal | cable_fault | B | 2026-09-11 | 2026-09-30 | 2.63
COR-GNW-CWA | COR-GNW-CWA-signal | interlocking_fault | C | 2026-09-04 | 2026-10-06 | 4.58 |  | 2026-09-14 10:15 | 2026-09-14 14:49
COR-RAU-HKH | COR-RAU-HKH-signal | interlocking_fault | A | 2026-09-02 | 2026-09-07 | 6.58 | 20 | 2026-09-12 14:30 | 2026-09-12 21:04
COR-NNU-RE | COR-NNU-RE-signal | interlocking_fault | C | 2026-09-04 | 2026-10-03 | 2.73 |  | 2026-09-16 11:15 | 2026-09-16 13:58
COR-RGP-GNP | COR-RGP-GNP-signal | interlocking_fault | C | 2026-09-05 | 2026-10-15 | 7.83
COR-TLMD-JLL | COR-TLMD-JLL-signal | signal_relay_fault | B | 2026-09-02 | 2026-09-12 | 3.99
COR-LMNR-INDM | COR-LMNR-INDM-signal | track_circuit_failure | B | 2026-09-10 | 2026-09-22 | 5.01 |  | 2026-09-16 01:30 | 2026-09-16 06:30
COR-SJV-GNK | COR-SJV-GNK-signal | track_circuit_failure | B | 2026-09-02 | 2026-09-16 | 6.89
COR-HDM-GNL | COR-HDM-GNL-signal | cable_fault | B | 2026-09-07 | 2026-09-18 | 5.64
COR-KKU-DNK | COR-KKU-DNK-signal | interlocking_fault | B | 2026-09-05 | 2026-09-23 | 7.48
COR-GHS-JWN | COR-GHS-JWN-signal | track_circuit_failure | C | 2026-09-05 | 2026-09-26 | 5.06
COR-CRV-KLD | COR-CRV-KLD-signal | track_circuit_failure | C | 2026-09-10 | 2026-10-01 | 2.6 |  | 2026-09-19 10:30 | 2026-09-19 13:06
COR-KAH-BET | COR-KAH-BET-signal | interlocking_fault | A | 2026-09-06 | 2026-09-13 | 6.09 | 15
COR-JHT-SCKR | COR-JHT-SCKR-signal | interlocking_fault | B | 2026-09-07 | 2026-09-19 | 6.69
COR-TRA-BTR | COR-TRA-BTR-signal | cable_fault | C | 2026-09-01 | 2026-09-21 | 2.58
COR-TLO-KHN | COR-TLO-KHN-signal | signal_relay_fault | C | 2026-09-05 | 2026-10-14 | 3.23
COR-UMNR-KGG | COR-UMNR-KGG-signal | signal_relay_fault | C | 2026-09-10 | 2026-10-17 | 4.56 |  | 2026-09-16 00:15 | 2026-09-16 04:48