## TRD_backlog
corridor_id | asset_id | defect_type | severity_code | detected_date | due_date | estimated_block_hours | speed_restriction_kmph | requested_window_start | requested_window_end
COR-KBH-KHTG | COR-KBH-KHTG-ohe_mast | insulator_flashover_risk | A | 2026-09-04 | 2026-09-11 | 2.29 | 15
COR-RNL-DDE | COR-RNL-DDE-ohe_mast | ohe_wire_wear | C | 2026-09-07 | 2026-10-15 | 2.92
COR-LBA-MWP | COR-LBA-MWP-ohe_mast | ohe_wire_wear | C | 2026-09-10 | 2026-10-05 | 1.89 |  | 2026-09-14 23:15 | 2026-09-15 01:08
COR-PLV-WTR | COR-PLV-WTR-ohe_mast | insulator_flashover_risk | B | 2026-09-02 | 2026-09-19 | 3.17 |  | 2026-09-14 23:30 | 2026-09-15 02:40
COR-SVZ-BKSA | COR-SVZ-BKSA-ohe_mast | insulator_flashover_risk | C | 2026-09-11 | 2026-10-14 | 3.98
COR-PDNR-LHN | COR-PDNR-LHN-ohe_mast | ohe_wire_wear | C | 2026-09-11 | 2026-10-15 | 3.56
COR-BSR-JCNR | COR-BSR-JCNR-ohe_mast | ohe_wire_wear | C | 2026-09-12 | 2026-10-03 | 2.47 |  | 2026-09-13 23:15 | 2026-09-14 01:43
COR-ISH-NOI | COR-ISH-NOI-ohe_mast | insulator_flashover_risk | B | 2026-09-02 | 2026-09-15 | 3.62 |  | 2026-09-14 00:30 | 2026-09-14 04:07
COR-UMED-SWF | COR-UMED-SWF-ohe_mast | feeder_fault | A | 2026-09-11 | 2026-09-21 | 3.67 | 15 | 2026-09-14 23:00 | 2026-09-15 02:40
COR-GNJ-KNP | COR-GNJ-KNP-ohe_mast | feeder_fault | C | 2026-09-11 | 2026-10-22 | 2.17
COR-MDPD-SRPM | COR-MDPD-SRPM-ohe_mast | traction_transformer_fault | C | 2026-09-05 | 2026-09-27 | 4.99
COR-BLND-KUPR | COR-BLND-KUPR-ohe_mast | traction_transformer_fault | A | 2026-09-08 | 2026-09-15 | 2.91 | 20
COR-MGC-MUE | COR-MGC-MUE-ohe_mast | ohe_wire_wear | B | 2026-09-03 | 2026-09-23 | 1.96
COR-NRK-GDN | COR-NRK-GDN-ohe_mast | traction_transformer_fault | A | 2026-09-10 | 2026-09-16 | 4.11 | 20
COR-DMA-BURN | COR-DMA-BURN-ohe_mast | feeder_fault | C | 2026-09-02 | 2026-10-08 | 2.45
COR-PRTP-MTC | COR-PRTP-MTC-ohe_mast | ohe_wire_wear | A | 2026-09-10 | 2026-09-17 | 1.9 | 30
COR-DPU-NLN | COR-DPU-NLN-ohe_mast | insulator_flashover_risk | A | 2026-09-07 | 2026-09-17 | 3.91 | 30
COR-RNL-DDE | COR-RNL-DDE-ohe_mast | traction_transformer_fault | B | 2026-09-03 | 2026-09-15 | 4.08 |  | 2026-09-14 00:30 | 2026-09-14 04:34
COR-MZU-PCV | COR-MZU-PCV-ohe_mast | feeder_fault | A | 2026-09-01 | 2026-09-06 | 1.83 | 15
COR-SHIV-ALN | COR-SHIV-ALN-ohe_mast | traction_transformer_fault | A | 2026-09-11 | 2026-09-17 | 3.67 | 30 | 2026-09-17 10:30 | 2026-09-17 14:10
COR-BVI-DIC | COR-BVI-DIC-ohe_mast | insulator_flashover_risk | A | 2026-09-04 | 2026-09-09 | 1.56 | 15 | 2026-09-13 02:15 | 2026-09-13 03:48
COR-BISH-JOR | COR-BISH-JOR-ohe_mast | traction_transformer_fault | C | 2026-09-04 | 2026-10-12 | 2.46 |  | 2026-09-17 11:00 | 2026-09-17 13:27
COR-MGO-CNHL | COR-MGO-CNHL-ohe_mast | traction_transformer_fault | A | 2026-09-08 | 2026-09-16 | 2.49 | 20 | 2026-09-16 14:15 | 2026-09-16 16:44
COR-HLR-KPA | COR-HLR-KPA-ohe_mast | ohe_wire_wear | C | 2026-09-05 | 2026-10-02 | 3.18
COR-DMA-BURN | COR-DMA-BURN-ohe_mast | ohe_wire_wear | B | 2026-09-07 | 2026-09-21 | 1.62 |  | 2026-09-19 01:00 | 2026-09-19 02:37
COR-KBH-KHTG | COR-KBH-KHTG-ohe_mast | ohe_wire_wear | A | 2026-09-11 | 2026-09-17 | 3.87 | 30
COR-BNKI-HPI | COR-BNKI-HPI-ohe_mast | traction_transformer_fault | B | 2026-09-01 | 2026-09-20 | 3.57 |  | 2026-09-16 10:30 | 2026-09-16 14:04
COR-NRK-GDN | COR-NRK-GDN-ohe_mast | feeder_fault | A | 2026-09-11 | 2026-09-19 | 4.8 | 15 | 2026-09-16 01:00 | 2026-09-16 05:48
COR-SVZ-BKSA | COR-SVZ-BKSA-ohe_mast | feeder_fault | B | 2026-09-06 | 2026-09-17 | 4.87 |  | 2026-09-13 10:30 | 2026-09-13 15:22
COR-KBH-KHTG | COR-KBH-KHTG-ohe_mast | ohe_wire_wear | B | 2026-09-12 | 2026-09-30 | 3.21 |  | 2026-09-19 00:30 | 2026-09-19 03:42
COR-KDH-TGH | COR-KDH-TGH-ohe_mast | insulator_flashover_risk | C | 2026-09-10 | 2026-10-24 | 2.27
COR-KHTG-KBH | COR-KHTG-KBH-ohe_mast | insulator_flashover_risk | B | 2026-09-10 | 2026-09-28 | 3.86
COR-RGJI-DPRA | COR-RGJI-DPRA-ohe_mast | insulator_flashover_risk | C | 2026-09-03 | 2026-09-29 | 1.83
COR-KBH-KHTG | COR-KBH-KHTG-ohe_mast | ohe_wire_wear | A | 2026-09-09 | 2026-09-17 | 3.42 | 30 | 2026-09-16 00:30 | 2026-09-16 03:55
COR-DTF-GOS | COR-DTF-GOS-ohe_mast | feeder_fault | A | 2026-09-04 | 2026-09-10 | 4.15 | 15 | 2026-09-13 11:15 | 2026-09-13 15:24
COR-MQX-GHQ | COR-MQX-GHQ-ohe_mast | ohe_wire_wear | B | 2026-09-09 | 2026-09-27 | 2.41
COR-EKH-SRY | COR-EKH-SRY-ohe_mast | traction_transformer_fault | C | 2026-09-11 | 2026-10-04 | 4.87 |  | 2026-09-17 22:15 | 2026-09-18 03:07
COR-KDH-TGH | COR-KDH-TGH-ohe_mast | feeder_fault | B | 2026-09-04 | 2026-09-22 | 4.84
COR-GNJ-KNP | COR-GNJ-KNP-ohe_mast | insulator_flashover_risk | A | 2026-09-02 | 2026-09-10 | 3.46 | 20
COR-DHRY-HJI | COR-DHRY-HJI-ohe_mast | feeder_fault | B | 2026-09-05 | 2026-09-24 | 2.64
COR-KHTG-KBH | COR-KHTG-KBH-ohe_mast | traction_transformer_fault | B | 2026-09-01 | 2026-09-16 | 2.46
COR-AMC-BTGH | COR-AMC-BTGH-ohe_mast | insulator_flashover_risk | C | 2026-09-09 | 2026-10-19 | 4.97
COR-TIS-GAG | COR-TIS-GAG-ohe_mast | insulator_flashover_risk | C | 2026-09-05 | 2026-10-10 | 4.05
COR-IDJ-KNP | COR-IDJ-KNP-ohe_mast | insulator_flashover_risk | A | 2026-09-07 | 2026-09-17 | 2.4 | 30 | 2026-09-16 23:00 | 2026-09-17 01:24
COR-DMA-BURN | COR-DMA-BURN-ohe_mast | feeder_fault | B | 2026-09-07 | 2026-09-21 | 3.01 |  | 2026-09-17 00:15 | 2026-09-17 03:15
COR-KLJI-CLKA | COR-KLJI-CLKA-ohe_mast | insulator_flashover_risk | C | 2026-09-08 | 2026-10-10 | 3.07
COR-KDHA-VRG | COR-KDHA-VRG-ohe_mast | ohe_wire_wear | B | 2026-09-01 | 2026-09-13 | 2.6
COR-TVNL-KDMD | COR-TVNL-KDMD-ohe_mast | insulator_flashover_risk | C | 2026-09-04 | 2026-10-13 | 4.51 |  | 2026-09-21 11:00 | 2026-09-21 15:30
COR-GAG-KITA | COR-GAG-KITA-ohe_mast | traction_transformer_fault | C | 2026-09-11 | 2026-10-10 | 1.92
COR-NBS-NCB | COR-NBS-NCB-ohe_mast | insulator_flashover_risk | A | 2026-09-02 | 2026-09-07 | 1.94 | 15 | 2026-09-13 11:15 | 2026-09-13 13:11
COR-GNGD-KUU | COR-GNGD-KUU-ohe_mast | insulator_flashover_risk | C | 2026-09-09 | 2026-10-06 | 3.01 |  | 2026-09-15 01:15 | 2026-09-15 04:15
COR-KBH-KHTG | COR-KBH-KHTG-ohe_mast | feeder_fault | B | 2026-09-03 | 2026-09-23 | 1.78 |  | 2026-09-19 22:15 | 2026-09-20 00:01
COR-RPH-MLV | COR-RPH-MLV-ohe_mast | ohe_wire_wear | C | 2026-09-08 | 2026-10-21 | 4.42 |  | 2026-09-20 02:15 | 2026-09-20 06:40
COR-KDHA-VRG | COR-KDHA-VRG-ohe_mast | feeder_fault | B | 2026-09-05 | 2026-09-15 | 2.23
COR-BCQ-STN | COR-BCQ-STN-ohe_mast | traction_transformer_fault | B | 2026-09-07 | 2026-09-23 | 4.95
COR-GKD-BDHA | COR-GKD-BDHA-ohe_mast | feeder_fault | C | 2026-09-01 | 2026-10-08 | 4.88 |  | 2026-09-15 22:15 | 2026-09-16 03:07
COR-SBI-SBT | COR-SBI-SBT-ohe_mast | ohe_wire_wear | A | 2026-09-07 | 2026-09-17 | 3.61 | 15
COR-DOR-MNKB | COR-DOR-MNKB-ohe_mast | feeder_fault | A | 2026-09-05 | 2026-09-15 | 3.68 | 20 | 2026-09-13 23:15 | 2026-09-14 02:55
COR-RES-SGJ | COR-RES-SGJ-ohe_mast | feeder_fault | A | 2026-09-02 | 2026-09-11 | 4.52 | 20
COR-VM-MYP | COR-VM-MYP-ohe_mast | insulator_flashover_risk | C | 2026-09-04 | 2026-09-25 | 4.8
COR-NRK-GDN | COR-NRK-GDN-ohe_mast | feeder_fault | B | 2026-09-03 | 2026-09-18 | 3.67
COR-MSK-MNE | COR-MSK-MNE-ohe_mast | traction_transformer_fault | B | 2026-09-08 | 2026-09-18 | 3.66 |  | 2026-09-14 00:30 | 2026-09-14 04:09
COR-SHIV-ALN | COR-SHIV-ALN-ohe_mast | ohe_wire_wear | A | 2026-09-07 | 2026-09-17 | 2.99 | 20
COR-NBS-NCB | COR-NBS-NCB-ohe_mast | traction_transformer_fault | B | 2026-09-10 | 2026-09-28 | 2.93
COR-ISH-NOI | COR-ISH-NOI-ohe_mast | traction_transformer_fault | C | 2026-09-12 | 2026-10-27 | 2.98
COR-JU-BGKT | COR-JU-BGKT-ohe_mast | feeder_fault | C | 2026-09-08 | 2026-10-01 | 4.39
COR-CUE-TISI | COR-CUE-TISI-ohe_mast | traction_transformer_fault | C | 2026-09-12 | 2026-10-04 | 4.9
COR-DCK-HLB | COR-DCK-HLB-ohe_mast | ohe_wire_wear | C | 2026-09-07 | 2026-10-22 | 1.5
COR-SVZ-BKSA | COR-SVZ-BKSA-ohe_mast | feeder_fault | C | 2026-09-07 | 2026-10-02 | 4.43 |  | 2026-09-15 14:15 | 2026-09-15 18:40
COR-KDH-TGH | COR-KDH-TGH-ohe_mast | feeder_fault | C | 2026-09-05 | 2026-10-07 | 3.67
COR-PVU-MYY | COR-PVU-MYY-ohe_mast | feeder_fault | C | 2026-09-02 | 2026-10-03 | 2.69
COR-PRKH-PCH | COR-PRKH-PCH-ohe_mast | traction_transformer_fault | B | 2026-09-10 | 2026-09-22 | 3.11 |  | 2026-09-16 10:30 | 2026-09-16 13:36
COR-SBI-SBT | COR-SBI-SBT-ohe_mast | feeder_fault | B | 2026-09-01 | 2026-09-18 | 3.73
COR-CTL-LDU | COR-CTL-LDU-ohe_mast | feeder_fault | B | 2026-09-10 | 2026-09-25 | 2.09
COR-RHW-KUP | COR-RHW-KUP-ohe_mast | feeder_fault | C | 2026-09-03 | 2026-10-07 | 5 |  | 2026-09-17 02:15 | 2026-09-17 07:15
COR-LMP-OEL | COR-LMP-OEL-ohe_mast | insulator_flashover_risk | A | 2026-09-11 | 2026-09-16 | 2.67 | 30
COR-KHDI-PDH | COR-KHDI-PDH-ohe_mast | feeder_fault | B | 2026-09-05 | 2026-09-18 | 2.11
COR-DHRY-HJI | COR-DHRY-HJI-ohe_mast | traction_transformer_fault | C | 2026-09-06 | 2026-09-26 | 3.92
COR-BRLF-LMG | COR-BRLF-LMG-ohe_mast | traction_transformer_fault | C | 2026-09-10 | 2026-10-15 | 3.46
COR-CMA-JTTN | COR-CMA-JTTN-ohe_mast | insulator_flashover_risk | C | 2026-09-01 | 2026-10-12 | 4.73 |  | 2026-09-17 01:30 | 2026-09-17 06:13
COR-SFY-CAZ | COR-SFY-CAZ-ohe_mast | insulator_flashover_risk | C | 2026-09-07 | 2026-10-07 | 1.59 |  | 2026-09-19 00:15 | 2026-09-19 01:50
COR-CNC-RBG | COR-CNC-RBG-ohe_mast | ohe_wire_wear | B | 2026-09-08 | 2026-09-27 | 3.93 |  | 2026-09-16 23:15 | 2026-09-17 03:10
COR-ISH-NOI | COR-ISH-NOI-ohe_mast | traction_transformer_fault | B | 2026-09-04 | 2026-09-18 | 4.24
COR-USD-DSD | COR-USD-DSD-ohe_mast | traction_transformer_fault | C | 2026-09-02 | 2026-10-10 | 4.65 |  | 2026-09-22 02:30 | 2026-09-22 07:09
COR-SFK-BUDM | COR-SFK-BUDM-ohe_mast | ohe_wire_wear | C | 2026-09-05 | 2026-10-10 | 4.11 |  | 2026-09-13 01:00 | 2026-09-13 05:06
COR-CRR-KUE | COR-CRR-KUE-ohe_mast | ohe_wire_wear | A | 2026-09-10 | 2026-09-19 | 3.58 | 20 | 2026-09-19 14:00 | 2026-09-19 17:34
COR-KHTG-KBH | COR-KHTG-KBH-ohe_mast | traction_transformer_fault | B | 2026-09-02 | 2026-09-13 | 4.24
COR-KHTG-KBH | COR-KHTG-KBH-ohe_mast | insulator_flashover_risk | B | 2026-09-02 | 2026-09-22 | 1.94 |  | 2026-09-15 23:15 | 2026-09-16 01:11
COR-MJGP-KMZ | COR-MJGP-KMZ-ohe_mast | traction_transformer_fault | C | 2026-09-12 | 2026-10-24 | 4.44
COR-NBS-NCB | COR-NBS-NCB-ohe_mast | ohe_wire_wear | B | 2026-09-06 | 2026-09-24 | 1.68
COR-GAG-KITA | COR-GAG-KITA-ohe_mast | ohe_wire_wear | A | 2026-09-11 | 2026-09-16 | 4.66 | 15
COR-SXT-SAMT | COR-SXT-SAMT-ohe_mast | traction_transformer_fault | B | 2026-09-05 | 2026-09-16 | 1.63
COR-BRPK-NBE | COR-BRPK-NBE-ohe_mast | insulator_flashover_risk | C | 2026-09-06 | 2026-10-02 | 2.65 |  | 2026-09-20 00:00 | 2026-09-20 02:39
COR-MTN-SIN | COR-MTN-SIN-ohe_mast | insulator_flashover_risk | B | 2026-09-01 | 2026-09-15 | 1.7 |  | 2026-09-14 02:15 | 2026-09-14 03:57
COR-BP-PTF | COR-BP-PTF-ohe_mast | insulator_flashover_risk | A | 2026-09-08 | 2026-09-18 | 4.42 | 15
COR-USD-DSD | COR-USD-DSD-ohe_mast | traction_transformer_fault | C | 2026-09-03 | 2026-09-25 | 2.52 |  | 2026-09-22 14:15 | 2026-09-22 16:46
COR-KHTG-KBH | COR-KHTG-KBH-ohe_mast | traction_transformer_fault | C | 2026-09-02 | 2026-09-24 | 1.89
COR-BRLF-LMG | COR-BRLF-LMG-ohe_mast | ohe_wire_wear | B | 2026-09-02 | 2026-09-22 | 3.25
COR-KVA-UTL | COR-KVA-UTL-ohe_mast | feeder_fault | A | 2026-09-08 | 2026-09-16 | 3.35 | 15
COR-BSR-JCNR | COR-BSR-JCNR-ohe_mast | insulator_flashover_risk | C | 2026-09-09 | 2026-10-09 | 3.68